## Dev Domain
Dev Domain Build Checklist
Rev2 - 02.15.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/full%20dev%20system%20build%20doc
RRAS
Build RRAS VM
Configure ethernet adapters for E1000 (not vmxnet)
Set internal nic adapter to 192.168.0.1
Install and configure RRAS role
AD1
Build AD1 VM
Set nic to 192.168.0.10
Install ADDS and DNS Roles
Install DHCP Role
Install ADCS - Enterprise Root
CA0
Build CA0 VM
Install ADCS - Standalone Root
CAS
Build CAS VM
Copy down SCCM install files, extract, run script
Primary Site
Build Primary Site Server VM
Copy down SCCM install files, extract, run script
Follow Primary Site Checklist (Worksheet 2)
Round 1 Testing
Image a VM /w PXE Boot
Push an application to a VM
SUP Role
Follow SUP Role Checklist
Test a software update
EPP Role
Follow EPP Role Checklist
Test an EPP Policy Push
Application Catalog Role
Follow App Catalog Checklist
Test an App Catalog installation

## Prod_Site Server
SCCM Site Server Install /w PKI Checklist
Rev7 - 02.20.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/site%20install%20doc%20v2
Department Firewall and Domain Config
Choose IP for site server
Internal DNS entry for site server
External (world) DNS entry for site server
Ports 443 and 80 open from\to world - to\from site server
Ports 3389 open from\to support-08.chemistry to\from site server
SRV Records for domain-trust published in DNS
Open DC's and Site Server to ASC DC's and ASC CAS
Publish SCCM SRV Record for site
VM Configuration
2 CPU's, 4GB Ram, Paravirtual SCSI driver, VMXNet3 Nic Driver
Drives configured - C Drive @ 100GB, D Drive @ 30GB, E Drive @ 17GB, F Drive at 100GB
WDDM Video Driver installed
CPU\RAM Hot-Add Enabled
VM Logging disabled (Options -> Advanced -> General -> Logging)
Boot time delay to 7000ms
OS and Prereq Install
Install and patch windows on the VM
X | Install .Net 4 Extended
X | Install Roles with Install-SCCMRoles script.
X | Run Create-SCCMShares script
Pre-Install AD Work
X | Run SCCM Group Creation Script
X | Give the site server full control of the systems management container and children
Create SCCM Certificate Templates
Copy the Client Install script to \\domain\netlogon
Modify the Client Install script's XML configuration file to suit your site.
Distribute the ASC Offline Root CA certificate to trusted roots on all domain PC's.
Create a GPO that enables certificate auto-enroll and startup script scoped to XP machines /w hotfix
Create a GPO that enables certificate auto-enroll and startup script scoped to Vista+ machines
Create an OU to accept newly imaged SCCM computers.
Create a scheduled task to run the Add-OUComputersToGroup script on site server
Add users and admins to the SCCM Users and SCCM Admins groups
Install Certificate Authority Role
X | Configure and run Install-SCCMSiteServerCA.cmd
Issue the Site Server a CA certificate from the Offline root and install it on the site server's CA.
Grant the Site Server CA Permission to Issue Certificates from the SCCM Templates
Request a SCCM Web Server Certificate for the Site Server
Request a SCCM Distribution Point Certificate for the Site Server
Add the SCCM Web Server Cert to the https bindings on the default and WSUS websites in IIS
Create a scheduled task to run the Revoke-DuplicateCertificates script on the site server.
Verify the site server PKI structure with PKIView.msc
Install SCCM
X | Install SQL Server 2008 R2 from script
X | Configure SQL TCP/IP on loopback and ipv4 interface
X | Configure Maximum SQL instance RAM to 2GB
X | Install WSUS and hotfix from script
X | Configure the WSUS http binding in IIS to use the SCCM web server certificate
X | Disable the host firewall
X | Install SCCM
X | Install the Admin Console
X | Upgrade site server, console, and client to CU2
X | Install MDT 2012
X | Configure Webdav and Directory Browsing with script
Integrate MDT with SCCM
CAS-Admin Configuration - These steps are done by the ASC Folk
X | Create security scopes
X | Create initial folders and collections
X | Assign RBAC permissions to the initial collections and scopes.
X | Create Site Boundary Group
X | Assign security scopes to site, site server, distribution point, and boundary group
Post-Install Configuration
Create site boundaries
Enable site AD publishing
Configure client communication to use certificates with dn string of department OU
Add Internet FQDN to the Management Point and Enable Internet Mode
Install the Distribution Point Certificate
Set the Network Access Account
Enable user and group discoveries
Create a Test Computers Collection
Assign PowerUsers Permissions to the Test Computers Collection

## SUP Role
SCCM Dev Site SUP Role Checklist
Rev3 - 02.20.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/software%20update%20point%20checklist
CAS Changes
X | Install WSUS and Hotfix on CAS
X | Install SUP Role on CAS
X | Run a full WSUS Synchronization
X | Enable SUP Internet Mode on CAS
Site Server Changes
Install WSUS and Hotfix on Site Server
Install SUP Role on Site Server
Create Update Collections with Scripts
Configure Software Inventory
X | Create Initial Software Update Groups
Download Initial Software Update Groups
Deploy Initial Software Update Groups
Create and Deploy 0-Day and 14-Day SUG's
Populate Update Collections with devices
Create and Run ADR's
Secure the update collections from mistaken deployments (IMPORTANT)
Enable SUP Internet Mode on Site Server
Configure Group Policy for SCCM Updates

## EPP Role
SCCM Endpoint Protection Role Checklist
Rev1 - 02.20.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/endpoint%20protection%20point%20checklist
CAS Changes
X | Install EPP Role on the CAS
Site Server Changes
Install and Configure the SUP Role first.
Create EPP Collections
Configure and Deploy Custom Anti-Malware Policies
Configure and Deploy Client Settings
Create Endpoint ADR's
Deploy Endopint SUG's.

## SP1 Update
SCCM SP1 Upgrade Checklist
Rev4 - 02.26.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/SCCM/sp1%20upgrade%20-%20cas
CAS Changes
Configure Site Backups
Spin Up a SQL Server Test VM
Test the Database Upgrade
Disable Site Maintenance Task
Backup Boot Image Customizations
Upgrade from WAIK to ADK
Install WSUS Hotfix
Run the Prereq Checker
Run the SP1 Install
Port-Install Testing
Build new WinPE 4 Boot Images
Test image deployment
Test software updates through the software update point
Test the application catalog
Final Work
Update SCCM Console to SP1 on all workstations\servers which have it installed.
Update the client startup script to install SP1

## SP1 Rollback Checklist
SCCM SP1 Uninstall \ Rollback Checklist
Rev1 - 02.27.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/sp1%20rollback
Tasks
Backup and Clear Current Database
Run Site Recovery
Run Site Replication Analyzer

## App Catalog
SCCM Application Catalog Checklist
Rev1 - 02.26.13 - puskar.4
Notes are available for any tasks highlighted in green at the following link:
https://wiki.chemistry.ohio-state.edu/sccm/application%20catalog%20point%20checklist
Site Server Changes
Configure WCF and ASP IIS Integration
Install Application Catalog Point Roles
Configure IIS Redirection
Configure Trusted Sites
Troubleshooting

## Reference
John Puskar
johnpuskar@gmail.com
github: jpuskar
windowsmasher.wordpress.com